## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Ctrl + Alt + Defeat | Completed | 46
Project title | Phehello Secondary Online Enrolment System | In Progress | 0
Stakeholder or organisation | Phehello Secondary School | Not Started | 0
Group mentor | Mr Elton Mokoduwe | Delayed | 0
Reporting phase | Unit 4 / Phase 3 | Blocked | 0
Reporting period | 28 September 2026 to 25 October 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Updated and completed the SRS and Developed and integrated the Flutter parent enrolment app and the ASP.NET staff web app on a shared Supabase backend, covering application submission, document and proof-of-payment upload, staff review, payment verification and confirmation letters. | Contribution entries | 18
Main challenge | Making both apps work safely on one Supabase database, because row-level security and file-storage rules blocked cross-role actions unti][ | Verified entries | 18
Next planned activity | Phase 3 final presentation | Unverified entries | 0
|  | Stakeholder engagements | 5

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
1.1 | Unit 1 / Phase 1 | Stakeholder engagement & problem identification | Initial engagement with the stakeholder to identify the current enrolment problem and understand the need for the proposed system. | David Adegbola | 2026-08-17 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
1.2 | Unit 1 / Phase 1 | Current-process analysis & requirements gathering | Analysed the existing enrolment process and gathered the initial requirements needed for the proposed online enrolment system | Paballo Lebusa | 2026-08-17 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
1.3 | Unit 1 / Phase 1 | Draft initial SRS | Prepared the initial Software Requirements Specification based on the identified stakeholder problem, current process and gathered requirements. | Mamello Lepitla | 2026-08-20 | 2026-08-20 | Completed | 100 |  | Yes |  | Completed
1.4 | Unit 1 / Phase 1 | Formal Stakeholder interview | Conducted a formal interview with the stakeholder to validate the existing enrolment process, identify challenges , and confirm system requirements. | All | 2026-08-24 | 2026-08-24 | Completed | 100 |  | Yes |  | Completed
1.5 | Unit 1 / Phase 1 | Update SRS with real interview findings | Updated the SRS using the findings from the formal interview, including confirmed stakeholder needs, process information and system requirements. | Mamello Lepitla | 2026-08-24 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
1.6 | Unit 1 / Phase 1 | Set up GitHub repository | Created the project GitHub repository for shared project documentation and development work. | Katleho Makhoali | 2026-08-22 | 2026-08-22 | Completed | 100 |  | Yes |  | Completed
1.7 | Unit 1 / Phase 1 | Setup Supabase project | Created and configured the Supabase project for the system backend. | Mamello Lepitla | 2026-08-26 | 2026-08-26 | Completed | 100 |  | No |  | Completed
1.8 | Unit 1 / Phase 1 | Unit 1 Progress Checkpoint submitted | Submitted the Unit 1 progress checkpoint containing required project progress materials. | Katleho Makhoali | 2026-08-26 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
1.9 | Unit 1 / Phase 1 | Feasibility study | Completed the technical , operational , economic , schedule, legal, and ethical feasibility | Lerato Mahlatsi, Paballo Lebusa | 2026-08-24 | 2026-08-28 | Completed | 100 |  | Yes |  | Completed
1.10 | Unit 1 / Phase 1 | Risk register & Mitigation planning | Identified project risks and developed appropriate mitigation strategies | Lerato Mahlatsi, Paballo Lebusa | 2026-08-24 | 2026-08-24 | Completed | 100 |  | Yes |  | Completed
1.11 | Unit 1 / Phase 1 | Baseline Microsoft Project Schedule | Created and baselined the Microsoft Project schedule showing project phases, tasks, dates, dependencies and responsibilities | Paballo Lebusa | 2026-08-27 | 2026-08-28 | Completed | 100 |  | Yes |  | Completed
1.12 | Unit 1 / Phase 1 | Compile Phase 1 Portfolio | Compiled the Phase 1 portfolio containing the SRS , feasibility study, risk register and reflection. | Mamello Lepitla | 2026-08-26 | 2026-08-31 | Completed | 100 |  | Yes |  | Completed
1.13 | Unit 1 / Phase 1 | Group Phase 1 reflection | Prepare the group's reflection on Phase 1, progress, contributions, challenges and lessons learned. | Paballo Lebusa | 2026-08-31 | 2026-08-31 | Completed | 100 |  | Yes |  | Completed
1.14 | Unit 1 / Phase 1 | Phase 1 Presentation | Prepare and deliver the phase 1 assessment presentation and defence | All | 2026-08-31 | 2026-09-04 | Completed | 100 |  | Yes |  | Completed
1.15 | Unit 3 / Phase 2 | System Architecture Diagram | Created the project system architecture design | Paballo Lebusa | 2026-09-07 | 2026-09-09 | Completed | 100 |  | Yes |  | Completed
1.16 | Unit 3 / Phase 2 | Use Case Diagram | Design the projects Use Case Diagram | Katleho Makhoali | 2026-09-10 | 2026-09-14 | Completed | 100 |  | Yes |  | Completed
1.17 | Unit 3 / Phase 2 | Sequence Diagram | Design the projects Sequence Diagram | Mpho Motaung, David Adegbola | 2026-09-09 | 2026-09-14 | Completed | 100 |  | Yes |  | Completed
1.18 | Unit 3 / Phase 2 | Entity Relationship Diagram | Design the ERD | Mamello Lepitla | 2026-09-07 | 2026-09-15 | Completed | 100 |  | Yes |  | Completed
1.19 | Unit 3 / Phase 2 | Flutter interface designs | Design the figma prototype for flutter | Lerato Mahlatsi,Mamello Lepitla, Paballo Lebusa | 2026-09-12 | 2026-09-16 | Completed | 100 |  | Yes |  | Completed
1.20 | Unit 3 / Phase 2 | ASP.NET interface design | Design the figma prototype for ASP.net | Lerato Mahlatsi,Mamello Lepitla, Paballo Lebusa | 2026-09-16 | 2026-09-20 | Completed | 100 |  | Yes |  | Completed
1.21 | Unit 3 / Phase 2 | Stakeholder feedback | Record the stakeholder feedback on the design | David Adegbola | 2026-09-14 | 2026-09-16 | Completed | 100 |  | Yes |  | Completed
1.22 | Unit 3 / Phase 2 | Microsoft project | fill the MS project schedule for phase 2 | Paballo Lebusa | 2026-09-14 | 2026-09-14 | Completed | 100 |  | Yes |  | Completed
1.23 | Unit 3 / Phase 2 | Github | Do the github documentation | Katleho Makhoali | 2026-09-17 | 2026-09-18 | Completed | 100 |  | Yes |  | Completed
1.24 | Unit 3 / Phase 2 | Project progress tracker | Fill in The tracker for phase 2 | Paballo Lebusa,Mamello Lepitla, Lerato Mahlatsi | 2026-09-14 | 2026-09-17 | Completed | 100 |  | Yes |  | Completed
1.25 | Unit 3 / Phase 2 | Updated SRS | Update the SRS for phase 2 | Mamello Lepitla | 2026-09-07 | 2026-09-22 | Completed | 100 |  | Yes |  | Completed
1.27 | Unit 4 / Phase 3 | Microsoft Project Schedule | Update the Microsoft Project Schedule for Phase 3 | Paballo Lebusa | 2026-10-02 | 2026-10-23 | Completed | 100 |  | Yes |  | Completed
1.28 | Unit 4 / Phase 3 | Progress Tracker | Update the Progress Tracker | Paballo Lebusa, Mamello Lepitla | 2026-10-02 | 2026-10-23 | Completed | 100 |  | Yes |  | Completed
1.29 | Unit 4 / Phase 3 | Github | Github documentation | Katleho Makhoali | 2026-10-02 | 2026-10-23 | Completed | 100 |  | Yes |  | Completed
1.30 | Unit 4 / Phase 3 | SRS | Updated the SRS(Part E) | Mamello Lepitla | 2026-10-02 | 2026-10-25 | Completed | 100 |  | Yes |  | Completed
1.31 | Unit 4 / Phase 3 | Supabase scheme and security policies | Implemented the database scheme, row-level security, storage policies and staff access policies for both apps. | Mamello Lepitla | 2026-10-02 | 2026-10-06 | Completed | 100 |  | Yes |  | Completed
1.32 | Unit 4 / Phase 3 | Flutter : registration, login and enrolment | Developed parent registration, login, the six-step enrolment wizard and document upload | Katleho Makhoali, Mpho Motaung, David Adegbola | 2026-10-06 | 2026-10-12 | Completed | 100 |  | Yes |  | Completed
1.33 | Unit 4 / Phase 3 | Flutter: payment information and proof of payment | Implemented the payment information screen an dproof-of-payment upolad with payment reference | Katleho Makhoali, Mpho Motaung, David Adegbola | 2026-10-12 | 2026-10-16 | Completed | 100 |  | Yes |  | Completed
1.34 | Unit 4 / Phase 3 | Flutter: status, notifications, profile and help | Built My Applications, Application Details, Messages and Notifications, Profile and Help & Support | Katleho Makhoali, Mpho Motaung, David Adegbola | 2026-10-13 | 2026-10-17 | Completed | 100 |  | Yes |  | Completed
1.35 | Unit 4 / Phase 3 | ASP.NET: login, dashboards and application lists | Developed staff login with role-based access, both dashboards and the application lists | Mamello Lepitla, Paballo Lebusa, Lerato Mahlatsi | 2026-10-12 | 2026-10-26 | Completed | 100 |  | Yes |  | Completed
1.36 | Unit 4 / Phase 3 | ASP.NET: login, dashboards and application lists | Developed the review page with approve, reject, request corrections and internal notes | Mamello Lepitla, Paballo Lebusa, Lerato Mahlatsi | 2026-10-13 | 2026-10-15 | Completed | 100 |  | Yes |  | Completed
1.37 | Unit 4 / Phase 3 | ASP.NET: payment verification | Developed clerk payment verification against the school payment records | Lerato Mahlatsi | 2026-10-12 | 2026-10-16 | Completed | 100 |  | Yes |  | Completed
1.38 | Unit 4 / Phase 3 | ASP.NET: messaging and reminders | Built the Message Parent and Send Deadline Reminder pages | Mamello Lepitla, Paballo Lebusa, Lerato Mahlatsi | 2026-10-13 | 2026-10-16 | Completed | 100 |  | Yes |  | Completed
1.39 | Unit 4 / Phase 3 | Confirmation letters | Implemented confirmation letter generation | Mamello Lepitla, Paballo Lebusa | 2026-10-13 | 2026-10-18 | Completed | 100 |  | Yes |  | Completed
1.40 | Unit 4 / Phase 3 | Delete application | Implemented parent deletion of an application with related records and files; Paballo wrote the database function | Katleho Makhoali, Mpho Motaung, David Adegbola, Paballo Lebusa | 2026-10-13 | 2026-10-18 | Completed | 100 |  | Yes |  | Completed
1.41 | Unit 4 / Phase 3 | Test data and sample documents | Prepared fictional learners, sample documents and school payment records | Mamello Lepitla | 2026-10-19 | 2026-10-19 | Completed | 100 |  | Yes |  | Completed
1.42 | Unit 4 / Phase 3 | Commit code to Github | Committed the Flutter and ASP.NET code. Each member committed from their own account after a lab-computer login problem | All | 2026-10-19 | 2026-10-21 | Completed | 100 |  | Yes |  | Completed
1.43 | Unit 4 / Phase 3 | Integration and testing | Tested the full flow from parent submission to staff review and payment verification, including role access tests | All | 2026-10-19 | 2026-10-23 | Completed | 100 |  | Yes |  | Completed
1.44 | Unit 4 / Phase 3 | Corrections after lecturer feedback | Clearer dashboard charts and a Save & Close button on the enrolment form | All | 2026-10-20 | 2026-10-23 | Completed | 100 |  | Yes |  | Completed
1.45 | Unit 4 / Phase 3 | Stakeholder confirmation of the developed system | Sent the confirmation form to the stakeholder and received it signed the same day | David Adegbola | 2026-10-23 | 2026-10-25 | Completed | 100 |  | Yes |  | Completed
1.46 | Unit 4 / Phase 3 | Final GitHub release, MS Project report and group reflection | Final repository release and final project report | Katleho Makhoali | 2026-10-19 | 2026-10-23 | Completed | 100 |  | Yes |  | Completed
1.47 | Unit 4 / Phase 3 | Final presentation and defence (Assessment 3) | Present and defend the system | All | 2026-10-26 | 2026-10-28 | Completed | 100 |  | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Mamello Lepitla | 222018199 | Unit 1 / Phase 1 | Supabase setup & SRS documentation | Backend setup and cocumentation | Set up Supabase project and completed /maintained the SRS and supporting documentation | 2026-08-31 |  | #VALUE! | Yes | 2026-08-31 | Major Phase 1 contribution
Katleho Makhoali | 224131387 | Unit 1 / Phase 1 | GitHub repository setup | GitHub setup | Set up and organised the project GitHub repository | 2026-08-23 |  | #VALUE! | Yes | 2026-08-26 | Repository setup
Paballo Lebusa | 221000537 | Unit 1 / Phase 1 | Project progress tracker and Microsoft project Scheduling | Progress tracking | Prepared and updated the ITC327W Project Progress Tracker | 2026-08-23 |  | #VALUE! | Yes | 2026-08-26 | Tracker maintenace
David Adegbola | 220042034 | Unit 1 / Phase 1 | Stakeholder communication | Stakeholder coordination | Assisted with communication and coordination relating to stakeholder engagement | 2026-08-19 |  | #VALUE! | Yes | 2026-08-19 | Stakeholder communication
Lerato Mahlatsi | 220049867 | Unit 1 / Phase 1 | Did the feasibility Study and risk analysis | Feasibility Study and Risk Analysis | Assisted with doing the feasibility Study and Risk Analysis | 2026-08-20 |  | #VALUE! | Yes | 2026-08-30 | Schedule supporting
Mpho Motaung | 224074632 | Unit 1 / Phase 1 | Group meetings/project participation | Group participation and assigned project activities | Attended group meetings but no specific project task or delivearble was personally completed during phase 1 |  | 0 | No contribution evidence available | Yes |  | No task volunteered for/ completed during Phase 1
Mamello Lepitla | 222018199 | Unit 3 / Phase 2 | SRS Documentation | Update the SRS documentation for Phase 2 | Did all the Documentation And also The Updated SRS | 2026-09-24 |  |  | Yes
Paballo Lebusa | 221000537 | Unit 3 / Phase 2 | System Architecture Diagram and Project progress tracker and MS Scheduling | Progress tracking and system architecture design | Updated the Project Tracker and Fixed the MS project Also Designed the System Architecture | 2026-09-09 |  |  | Yes
David Adegbola | 220042034 | Unit 3 / Phase 2 | Sequence diagram for ASP.NET | Did the Sequence Diagram for ASP.NET | Completed the Sequence Diagram For the ASP.NET | 2026-09-14 |  |  | Yes
Lerato Mahlatsi | 220049867 | Unit 3 / Phase 2 | Flutter and ASP.NET interface design | Design the Flutter and ASP.NET interface Design | Did the Interface designs but they were incomplete and was finished by Mamello Lepitla and Paballo Lebusa | 2026-09-20 |  |  | Yes
Katleho Makhoali | 224131387 | Unit 3 / Phase 2 | Use Case Diagram | Design the Use Case diagram and Github Documentation | Completed the Use Case for Both Parent and Admin and github Documentation | 2026-09-15 |  |  | Yes
Mpho Motaung | 224074632 | Unit 3 / Phase 2 | Sequence diagram for Flutter | Did the Sequence Diagram for Flutter | Completed the Sequence Diagram For the Flutter | 2026-09-14 |  |  | Yes
Mamello Lepitla | 222018199 | Unit 4 / Phase 3 | Supabase backend, ASP.NET staff features, test data, SRS | Backend security, payment and staff features, documentation | Implemented the Supabase schema, row-level security and storage policies. Worked on the payment information and proof-of-payment screens, the ASP.NET staff screens, application review and notes, and confirmation letters. Prepared the test data and updated the SRS (Part E). Took part in integration testing and committed work from her own GitHub account. | 2026-10-25 |  |  | Yes | 2026-10-19
Paballo Lebusa | 221000537 | Unit 4 / Phase 3 | Staff features, database fixes, Project schedule and tracker | Staff and payment features, project tracking | Worked on the ASP.NET staff screens, application review, confirmation letters and the payment screens. Wrote the staff access patch with Mamello and the database function for deleting applications. Updated the Microsoft Project schedule and the Progress Tracker. Took part in integration testing and committed from his own GitHub account. | 2026-10-23 |  |  | Yes | 2026-10-16
Katleho Makhoali | 224131387 | Unit 4 / Phase 3 | Flutter parent app, GitHub | Parent app development, GitHub documentation | Developed the Flutter registration, login, enrolment and status screens and the delete-application feature with Mpho and David. Wrote the GitHub documentation. Took part in integration testing and committed from his own GitHub account. | 2026-10-23 |  |  | Yes | 2026-10-17
David Adegbola | 220042034 | Unit 4 / Phase 3 | Flutter parent app, stakeholder communication | Parent app development, stakeholder coordination | Developed the Flutter enrolment screens and the delete-application feature with Katleho and Mpho. Contacted the stakeholder, sent the confirmation form and received the signed form on 25 Oct 2026. Took part in integration testing and committed from his own GitHub account. | 2026-10-25 |  |  | Yes | 2026-10-17
Lerato Mahlatsi | 220049867 | Unit 4 / Phase 3 | ASP.NET payment verification | Financial Clerk features | Developed the clerk payment verification against the school payment records and worked on the ASP.NET staff screens. Took part in integration testing and committed from her own GitHub account. | 2026-10-23 |  |  | Yes | 2026-10-15
Mpho Motaung | 224074632 | Unit 4 / Phase 3 | Flutter parent app | Parent app development | Developed the Flutter enrolment, status and notification screens and the delete-application feature with Katleho and David. Took part in integration testing and committed from his own GitHub account. | 2026-10-23 |  |  | Yes | 2026-10-17

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-20 | Unit 1 / Phase 1 | Online Meeting | Introduce the project and identify the school's current enrol | PIJ Lebusa, KI Makhoali, M Lepitla, M Motaung , DT Adegbola | Maleshoane Adegbola - Principal, Zukiswa Khondlo - Secretary | Stakeholder was confirmed and a date for formal interview was set. | Gather detailed requirements and arrange formal interview. | Appendex B
2026-08-24 | Unit 1 / Phase 1 | Online Meeting | Full formal stakeholder needs-assessment interview | KI Makhoali, PIJ Lebusa, M Lepitla, M Motaung, DT Adegbola, LR Mahlatsi | Zukiswa Khondlo - Secretary to the Principal who is the delegate representative | All the 12 interview questions were answered. All the findings were gathered and were also confirmed the same day. | Update the STS with the findings and proceed with feasibility and risk analysis | Appendex C
2026-09-14 | Unit 3 / Phase 2 | Whatsapp Meeting | Feedback on Figma Wireframes | David Adegbola | Zukiswa Khondlo - Secretary to the Principal who is the delegate representative | The Stakeholder Requested we Use Brown and White as the main colors of the interface | Update the flutter and ASP.NET wireframes using brown and white as the primary color scheme, with supporting neutral/accent colours where needed for readability and status indicators
2026-09-21 | Unit 3 / Phase 2 | Whatsapp Meeting | Feedback on Enrollment fee and School Banking Details | David Adegbola | Zukiswa Khondlo - Secretary to the Principal who is the delegate representative | Display the required enrollment fee and school banking details in the parent-facing payment step and allow parents to enter a payment reference before uploading the proof of payment | Added a dedicated Payment Information screen displaying the fee and banking details and updated proof of payment screen to capture the payment reference before the proof of payment document is uploaded
2026-10-23 | Unit4/Phase 3 | WhatsApp | Confirmation of the developed system | David Adegbola | Maleshoane Gweneth Adegbola)– Principal, Phehello Secondary School | Confirmation form sent and signed form received on the same day. | Insert the signed form in the SRS, Part E (Figure 4.72). | SRS Part E, Figure 4.79

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-19 | Unit 1 / Phase 1 | Coordinating stakeholder communication and arranging the formal interview required additional coordination. | Requirements validation depended on obtaining stakeholder feedback before the SRS could be finalised. | The group coordinated communication with the stakeholder and conducted the formal interview to obtain the required information. | DT Adegbola | 2026-08-25 | Resolved
2026-08-24 | Unit 1 / Phase 1 | A large portion of the project documentation had to be completed and maintained by one person | Increased the workload and time required to keep SRS and project documentation updated while other project activities were being completed. | Documentation was prioritized and was organised alongside the completion of the project activities to keep the project records up to date. | Mamello lepitla | 2026-08-31 | Resolved
2026-08-31 | Unit 1 / Phase 1 | Uneven participation among group members affected the distribution of project tasks. | Some tasks had to be handled by fewer active members, increasing the workload and requiring additional coordination. | Actual contributions were documented in the progress tracker, and responsibilities were clarified according to the work being completed. | All members | 2026-09-04 | Resolved
2026-09-11 | Unit 3 / Phase 2 | The Interface Design was left unfinished. | Some Students had to leave they work and fix the design | A new interface design was done by some members | Mamello lepitla, Paballo Lebusa |  | Resolved
2026-10-04 | Unit 4 / Phase 3 | Row-level security stopped staff and parents from doing what each role needed. | Some staff screens and uploads failed until access was fixed. | Wrote a staff access patch and per-role policies for tables and storage. | Paballo Lebusa, Mamello Lepitla | 2026-10-06 | Resolved
2026-10-16 | Unit 4 / Phase 3 | Parents could not delete an application because the tables have no cascading deletes and RLS blocked it. | Deletion was impossible from the app. | Created a database function that removes all related records in one transaction, plus storage delete policies. | Paballo Lebusa | 2026-10-18 | Resolved
2026-10-21 | Unit 4/Phase 3 | A member’s GitHub account was left signed in on a school lab computer, so a commit made from that computer showed that member’s name and the author could not be changed. | Commits were attributed to the wrong person, which could misrepresent who did the work. | Each member committed from their own GitHub account instead, so every contribution is recorded under the right name. | All members | 2026-10-21 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 4 / Phase 3 | Initial or updated SRS completed | Yes
Reporting period | 28 September 2026 - 25 October 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Flutter parent app, ASP.NET staff app, Supabase schema and policies, payment proof and verification, confirmation letters, delete application, test data and demonstration. | Stakeholder engagement recorded | Yes
What remains incomplete? | Nothing | Challenges and actions updated | Yes
Why is it incomplete? |  | Group reflection completed | Yes
Which contributions were particularly important? | Flutter parent app, ASP.NET staff app And supabase development and integration | Microsoft Project updated | Yes
Were there participation concerns? | Nothing | GitHub evidence available | Yes
What will the group improve in the next phase? | N/A | Confidential peer check completed | Yes
Main priority for the next phase | N/A

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 3 / Phase 2 | Length | Approximately 300–400 words in total.
Project title | Phehello Online Enrollments System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important lesson from Phase 3 was that security rules must be designed together with the features, not added afterwards. Almost every problem we met came from row-level security and storage policies in Supabase rather than from the screens. Features such as deleting an application touch many related tables and uploaded files, so they needed careful ordering and a database function instead of simple queries. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The work went well because the Phase 2 designs carried straight into development. The stakeholder’s request for brown and white colours, and for a payment step showing the fee, banking details and payment reference, was built into the Flutter parent app and the ASP.NET staff app. A shared Supabase backend gave both applications the same data, which made integration and testing easier. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The hardest parts were the access policies and the features that affect many records at once. Parents and staff need different permissions, and several screens and uploads failed until we corrected the policies. We learned to test each feature with both roles before calling it finished. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to each member’s strengths, with some members focusing on the parent app, others on the staff app and backend, and others on documentation, testing and project tracking. Contribution was not completely even, and some members had to take on extra work to keep deliverables on schedule. We recorded this in the contribution record..
Did all members contribute fairly? Explain. | We handled delays by redistributing work and following up through messages, and we had no major conflicts..
How did the group handle disagreements or delays? | We did not encounter major interpersonal conflicts, but external stakeholder delays and internal schedule delays and internal schedule mismatches disrupted our timelines. We adapted by rescheduling interviews, conducting asynchronous follow-ups, and redistributing critical drafting responsibilities to ensure project milestones and documentation requirements were met on time.
What did the group learn from the stakeholder? | From the stakeholder we learned that the school wants a simple, clear process that replaces the slow paper-based enrolment, and that payment details must be visible to parents before they upload proof of payment.
Improvement action 1 for the next phase | N/A
Improvement action 2 for the next phase | N/A
Priority for the next phase | N/A