## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Ctrl + Alt + Defeat | Completed
Project title | Phehello Secondary Online Enrolment System | In Progress
Stakeholder or organisation | Phehello Secondary School | Not Started
Group mentor | Mr Elton Mokoduwe | Delayed
Reporting phase | Unit 3 / Phase 2 | Blocked
Reporting period | 7 September to 25 September | Overdue
Overall status | Completed
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Updated the Complete SRS and The System Architecture and Design | Contribution entries
Main challenge | The Main Challenge was doing the figma interfaces | Verified entries
Next planned activity | Phase 2 | Unverified entries
Stakeholder engagements

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
1.1 | Unit 1 / Phase 1 | Stakeholder engagement & problem identification | Initial engagement with the stakeholder to identify the current enrolment problem and understand the need for the proposed system. | David Adegbola | 2026-08-17 | 2026-08-21 | Completed | 100 |  | Yes
1.2 | Unit 1 / Phase 1 | Current-process analysis & requirements gathering | Analysed the existing enrolment process and gathered the initial requirements needed for the proposed online enrolment system | Paballo Lebusa | 2026-08-17 | 2026-08-21 | Completed | 100 |  | Yes
1.3 | Unit 1 / Phase 1 | Draft initial SRS | Prepared the initial Software Requirements Specification based on the identified stakeholder problem, current process and gathered requirements. | Mamello Lepitla | 2026-08-20 | 2026-08-20 | Completed | 100 |  | Yes
1.4 | Unit 1 / Phase 1 | Formal Stakeholder interview | Conducted a formal interview with the stakeholder to validate the existing enrolment process, identify challenges , and confirm system requirements. | All | 2026-08-24 | 2026-08-24 | Completed | 100 |  | Yes
1.5 | Unit 1 / Phase 1 | Update SRS with real interview findings | Updated the SRS using the findings from the formal interview, including confirmed stakeholder needs, process information and system requirements. | Mamello Lepitla | 2026-08-24 | 2026-08-26 | Completed | 100 |  | Yes
1.6 | Unit 1 / Phase 1 | Set up GitHub repository | Created the project GitHub repository for shared project documentation and development work. | Katleho Makhoali | 2026-08-22 | 2026-08-22 | Completed | 100 |  | Yes
1.7 | Unit 1 / Phase 1 | Setup Supabase project | Created and configured the Supabase project for the system backend. | Mamello Lepitla | 2026-08-26 | 2026-08-26 | Completed | 100 |  | No
1.8 | Unit 1 / Phase 1 | Unit 1 Progress Checkpoint submitted | Submitted the Unit 1 progress checkpoint containing required project progress materials. | Katleho Makhoali | 2026-08-26 | 2026-08-26 | Completed | 100 |  | Yes
1.9 | Unit 1 / Phase 1 | Feasibility study | Completed the technical , operational , economic , schedule, legal, and ethical feasibility | Lerato Mahlatsi, Paballo Lebusa | 2026-08-24 | 2026-08-28 | Completed | 100 |  | Yes
1.10 | Unit 1 / Phase 1 | Risk register & Mitigation planning | Identified project risks and developed appropriate mitigation strategies | Lerato Mahlatsi, Paballo Lebusa | 2026-08-24 | 2026-08-24 | Completed | 100 |  | Yes
1.11 | Unit 1 / Phase 1 | Baseline Microsoft Project Schedule | Created and baselined the Microsoft Project schedule showing project phases, tasks, dates, dependencies and responsibilities | Paballo Lebusa | 2026-08-27 | 2026-08-28 | Completed | 100 |  | Yes
1.12 | Unit 1 / Phase 1 | Compile Phase 1 Portfolio | Compiled the Phase 1 portfolio containing the SRS , feasibility study, risk register and reflection. | Mamello Lepitla | 2026-08-26 | 2026-08-31 | Completed | 100 |  | Yes
1.13 | Unit 1 / Phase 1 | Group Phase 1 reflection | Prepare the group's reflection on Phase 1, progress, contributions, challenges and lessons learned. | Paballo Lebusa | 2026-08-31 | 2026-08-31 | Completed | 100 |  | Yes
1.14 | Unit 1 / Phase 1 | Phase 1 Presentation | Prepare and deliver the phase 1 assessment presentation and defence | All | 2026-08-31 | 2026-09-04 | Completed | 100 |  | Yes
1.15 | Unit 3 / Phase 2 | System Architecture Diagram | Created the project system architecture design | Paballo Lebusa | 2026-09-07 | 2026-09-09 | Completed | 100 |  | Yes
1.16 | Unit 3 / Phase 2 | Use Case Diagram | Design the projects Use Case Diagram | Katleho Makhoali | 2026-09-10 | 2026-09-14 | Completed | 100 |  | Yes
1.17 | Unit 3 / Phase 2 | Sequence Diagram | Design the projects Sequence Diagram | Mpho Motaung, David Adegbola | 2026-09-09 | 2026-09-14 | Completed | 100 |  | Yes
1.18 | Unit 3 / Phase 2 | Entity Relationship Diagram | Design the ERD | Mamello Lepitla | 2026-09-07 | 2026-09-15 | Completed | 100 |  | Yes
1.19 | Unit 3 / Phase 2 | Flutter interface designs | Design the figma prototype for flutter | Lerato Mahlatsi, Paballo Lebusa,Mamello Lepitla | 2026-09-12 | 2026-09-16 | Completed | 100 |  | Yes
1.2 | Unit 3 / Phase 2 | ASP.NET interface design | Design the figma prototype for ASP.net | Lerato Mahlatsi, Paballo Lebusa,Mamello Lepitla | 2026-09-16 | 2026-09-20 | Completed | 100 |  | Yes
1.21 | Unit 3 / Phase 2 | Stakeholder feedback | Record the stakeholder feedback on the design | David Adegbola | 2026-09-14 | 2026-09-16 | Completed | 100 |  | Yes
1.22 | Unit 3 / Phase 2 | Microsoft project | fill the MS project schedule for phase 2 | Paballo Lebusa | 2026-09-14 | 2026-09-14 | Completed | 100 |  | Yes
1.23 | Unit 3 / Phase 2 | Github | Do the github documentation | Katleho Makhoali | 2026-09-17 | 2026-09-18 | Completed | 100 |  | Yes
1.24 | Unit 3 / Phase 2 | Project progress tracker | Fill in The tracker for phase 2 | Paballo Lebusa | 2026-09-14 | 2026-09-17 | Completed | 75 |  | Yes
1.25 | Unit 3 / Phase 2 | Updated SRS | Update the SRS for phase 2 | Mamello Lepitla | 2026-09-07 | 2026-09-22 | Completed | 100 |  | Yes
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Mamello Lepitla | 222018199 | Unit 1 / Phase 1 | Supabase setup & SRS documentation | Backend setup and cocumentation | Set up Supabase project and completed /maintained the SRS and supporting documentation | 2026-08-31 |  | #VALUE! | Yes | 2026-08-31 | Major Phase 1 contribution
Katleho Makhoali | 224131387 | Unit 1 / Phase 1 | GitHub repository setup | GitHub setup | Set up and organised the project GitHub repository | 2026-08-23 |  | #VALUE! | Yes | 2026-08-26 | Repository setup
Paballo Lebusa | 221000537 | Unit 1 / Phase 1 | Project progress tracker and Microsoft project Scheduling | Progress tracking | Prepared and updated the ITC327W Project Progress Tracker | 2026-08-23 |  | #VALUE! | Yes | 2026-08-26 | Tracker maintenace
David Adegbola | 220042034 | Unit 1 / Phase 1 | Stakeholder communication | Stakeholder coordination | Assisted with communication and coordination relating to stakeholder engagement | 2026-08-19 |  | #VALUE! | Yes | 2026-08-19 | Stakeholder communication
Lerato Mahlatsi | 220049867 | Unit 1 / Phase 1 | Did the feasibility Study and risk analysis | Feasibility Study and Risk Analysis | Assisted with doing the feasibility Study and Risk Analysis | 2026-08-20 |  | #VALUE! | Yes | 2026-08-30 | Schedule supporting
Mpho Motaung | 224074632 | Unit 1 / Phase 1 | Group meetings/project participation | Group participation and assigned project activities | Attended group meetings but no specific project task or delivearble was personally completed during phase 1 |  | 0 | No contribution evidence available | Yes |  | No task volunteered for/ completed during Phase 1
Mamello Lepitla | 222018199 | Unit 3 / Phase 2 | SRS Documentation | Update the SRS documentation for Phase 2 | Did all the Documentation And also The Updated SRS | 2026-09-24 |  |  | Yes
Paballo Lebusa | 221000537 | Unit 3 / Phase 2 | System Architecture Diagram and Project progress tracker and MS Scheduling | Progress tracking and system architecture design | Updated the Project Tracker and Fixed the MS project Also Designed the System Architecture | 2026-09-09 |  |  | Yes
David Adegbola | 220042034 | Unit 3 / Phase 2 | Sequence diagram for ASP.NET | Did the Sequence Diagram for ASP.NET | Completed the Sequence Diagram For the ASP.NET | 2026-09-14 |  |  | Yes
Lerato Mahlatsi | 220049867 | Unit 3 / Phase 2 | Flutter and ASP.NET interface design | Design the Flutter and ASP.NET interface Design | Did the Interface designs but they were incomplete and was finished by Mamello Lepitla and Paballo Lebusa | 2026-09-20 |  |  | Yes
Katleho Makhoali | 224131387 | Unit 3 / Phase 2 | Use Case Diagram | Design the Use Case diagram and Github Documentation | Completed the Use Case for Both Parent and Admin and github Documentation | 2026-09-15 |  |  | Yes
Mpho Motaung | 224074632 | Unit 3 / Phase 2 | Sequence diagram for Flutter | Did the Sequence Diagram for Flutter | Completed the Sequence Diagram For the Flutter | 2026-09-14 |  |  | Yes

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-20 | Unit 1 / Phase 1 | Online Meeting | Introduce the project and identify the school's current enrol | PIJ Lebusa, KI Makhoali, M Lepitla, M Motaung , DT Adegbola | Maleshoane Adegbola - Principal, Zukiswa Khondlo - Secretary | Stakeholder was confirmed and a date for formal interview was set. | Gather detailed requirements and arrange formal interview. | Appendex B
2026-08-24 | Unit 1 / Phase 1 | Online Meeting | Full formal stakeholder needs-assessment interview | KI Makhoali, PIJ Lebusa, M Lepitla, M Motaung, DT Adegbola, LR Mahlatsi | Zukiswa Khondlo - Secretary to the Principal who is the delegate representative | All the 12 interview questions were answered. All the findings were gathered and were also confirmed the same day. | Update the STS with the findings and proceed with feasibility and risk analysis | Appendex C
2026-09-14 | Unit 3 / Phase 2 | Whatsapp Meeting | Feedback on Figma Wireframes | David Adegbola | Zukiswa Khondlo - Secretary to the Principal who is the delegate representative | The Stakeholder Requested we Use Brown and White as the main colors of the interface | Update the flutter and ASP.NET wireframes using brown and white as the primary color scheme, with supporting neutral/accent colours where needed for readability and status indicators
2026-09-21 | Unit 3 / Phase 2 | Whatsapp Meeting | Feedback on Enrollment fee and School Banking Details | David Adegbola | Zukiswa Khondlo - Secretary to the Principal who is the delegate representative | Display the required enrollment fee and school banking details in the parent-facing payment step and allow parents to enter a payment reference before uploading the proof of payment | Added a dedicated Payment Information screen displaying the fee and banking details and updated proof of payment screen to capture the payment reference before the proof of payment document is uploaded

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-19 | Unit 1 / Phase 1 | Coordinating stakeholder communication and arranging the formal interview required additional coordination. | Requirements validation depended on obtaining stakeholder feedback before the SRS could be finalised. | The group coordinated communication with the stakeholder and conducted the formal interview to obtain the required information. | DT Adegbola | 2026-08-25 | Resolved
2026-08-24 | Unit 1 / Phase 1 | A large portion of the project documentation had to be completed and maintained by one person | Increased the workload and time required to keep SRS and project documentation updated while other project activities were being completed. | Documentation was prioritized and was organised alongside the completion of the project activities to keep the project records up to date. | Mamello lepitla | 2026-08-31 | Resolved
2026-08-31 | Unit 1 / Phase 1 | Uneven participation among group members affected the distribution of project tasks. | Some tasks had to be handled by fewer active members, increasing the workload and requiring additional coordination. | Actual contributions were documented in the progress tracker, and responsibilities were clarified according to the work being completed. | All members | 2026-09-04 | Resolved
2026-09-11 | Unit 3 / Phase 2 | The Interface Design was left unfinished. | Some Students had to leave they work and fix the design | A new interface design was done by some members | Mamello lepitla, Paballo Lebusa

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 7- 25 September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | The System Architecture, ERD Table, Use Case Diagram, GitHub Documentation, Sequence Diagrams and Updated SRS Documentation | Stakeholder engagement recorded | Yes
What remains incomplete? | Nothing | Challenges and actions updated | Yes
Why is it incomplete? |  | Group reflection completed | Yes
Which contributions were particularly important? | The Progress Tracker and Updated SRS | Microsoft Project updated | Yes
Were there participation concerns? | Yes | GitHub evidence available | Yes
What will the group improve in the next phase? | Improve good group communication and address participation cooncerns | Confidential peer check completed | Yes
Main priority for the next phase | Developing the Prototypes

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 3 / Phase 2 | Length | Approximately 300–400 words in total.
Project title | Phehello Online Enrollments System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Because Flutter and ASP.NET both read and write directly to the same Supabase Authentication, Database and Storage APIs, any mismatch between the SRS, the sequence diagrams and the actual schema breaks something for both applications at once. Reviewing our schema against the approved sequence diagrams taught us to treat the ERD as a living document, not a one-off diagram. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Producing the Architecture Diagram, ERD, Use Case Diagrams and three Sequence Diagrams went well because work was split by strength and each diagram was checked against the others. Live stakeholder feedback was also incorporated smoothly: WhatsApp input on the colour scheme and on the enrolment fee/banking details became concrete changes, including a new Payment Information screen, within days. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The Use Case and Sequence Diagrams were hardest, particularly keeping three separate sequence diagrams aligned with the use case actors and the eventual database schema. The Flutter and ASP.NET interface designs were also left incomplete by the assigned member and had to be finished by others close to the deadline. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were split by strength: architecture and progress tracking (Paballo), SRS and database documentation (Mamello), Use Case diagrams and GitHub documentation (Katleho), sequence diagrams split between ASP.NET (David) and Flutter (Mpho), and interface design (Lerato, later supported by Mamello and Paballo).
Did all members contribute fairly? Explain. | Contribution was uneven. Most deliverables were completed and verified, but the interface design task was left unfinished by the assigned member and had to be picked up by others. Core members carried a larger share of the documentation and schema-review work needed to keep Phase 2 consistent.
How did the group handle disagreements or delays? | No major interpersonal conflicts occurred, but unfinished interface designs and the need to realign the schema with the sequence diagrams caused delays. These were resolved by reassigning the outstanding design work and documenting the database design decisions so the SRS, ERD and diagrams stayed consistent.
What did the group learn from the stakeholder? | The stakeholder gave fast, concrete feedback once asked directly: brown and white were confirmed as interface colours, and the R200 enrolment fee with FNB banking details were supplied for the Payment Information screen. Short, targeted WhatsApp check-ins worked better than waiting for scheduled meetings.
Improvement action 1 for the next phase | Assign and check interface design work earlier, with an interim review point, so an unfinished screen is caught and reassigned before it becomes a deadline risk.
Improvement action 2 for the next phase | Review the schema against the SRS and sequence diagrams continuously during development, rather than only at the end of the phase, to catch alignment issues earlier.
Priority for the next phase | Moving from design into development: building the Flutter and ASP.NET applications against the finalised ERD and sequence diagrams, and beginning integration testing through Supabase.